## Summary
Item | Cost
GEB Otla | 60351.606
STP Otla | 145420.6558
DG Otla | 132277.51
Tank near Kitchen | 15709.7405 | Unit rates | Unit | Rate
Wall near kitchen | 33333.12 | Masonry | cum | 6000
Bridge & Tent | 28347.1 | Single mala plaster | sqft | 30
Reception | 23960.307 | Double coat plaster | sqft | 45
Dining entrance | 26617.5216 | Slab casting | cum | 5000
Random flooring | 88313.1126 | Steel | kg | 90
Staff quarters bathroom | 22746.9264 | Wall tiles | sq ft | 80
Hari plumber | 4243.9677 | Kota | sq ft | 90
Room 10 Overflow channel repairing | 10250 | Green marble | sq ft | 110
Gym | 175805.203 | Fabrication | kg | 130
Tent Roof | 203320 | Damar sheet | sq ft | 23
Patra | 486200 | Patra | sq ft | 22
Damar sheet | 508300 | Manglorian tiles (labour) | sq ft | 34
Manglorian tiles (without material) | 746300 | Manglorian tiles (with material) | sq ft | 60
Manglorian tiles (only material) | 93600 | Water proofing | sq ft | 230
Swimming pool | 2060000 | Excavation | cum | 300
Heat pump | 19391.832 | Backfilling | cum | 150
China Mosiac | 697590 | PCC | cum | 3500
Kitchen | 1266234.0382 | Grade slab | cum | 4000
Spa old | 3316588.4845
Spa new | 1020983.5064
UGWT, Septic tank, Soakpit | 793000
Renovation - all rooms | 689000
Plumbing + Random outside all rooms | 70000
Plumbing material for kitchen | 0
Electric material for kitchen | 0
Electric labour for kitchen | 0
12737884.6316

## Renovation all rooms
Room 1 | 49000 | Otta
Room 2 | 39000
Room 3 | 42000 | Green marble
Room 4 | 41000 | Green marble
Room 5 | 44000
Room 6 | 39000
Room 7 | 44000
Room 8 | 39000
Room 9 | 38000
Room 10 | 38000
Room 11 | 38000
Room 12 | 57000 | Green marble
Room 13 | 63000 | Green marble
Room 14 | 39000
Dining | 36000
Reception | 43000
689000
Typical work
Kota
Vata
Ghasai
Otta

## Kitchen
| No. | L | B | H | Unit | Measurement | Rate | Total
Brickwork | 2 | 3 | 3 | 0.23 | cum | 4.14
| 1 | 0.74 | 3 | 0.23 | cum | 0.5106
| 1 | 1.09 | 0.81 | 0.23 | cum | 0.20307
| 1 | 0.23 | 0.23 | 3 | cum | 0.1587
| 1 | 1.1 | 3 | 0.23 | cum | 0.759
| 1 | 0.701 | 0.23 | 3 | cum | 0.48369
| 1 | 0.3 | 0.23 | 3 | cum | 0.207
| 1 | 1 | 1 | 0.23 | cum | 0.23
| 3 | 3 | 3 | 0.23 | cum | 6.21
| 3 | 3 | 2.2 | 0.35 | cum | 6.93
| 1 | 8.5 | 3 | 0.23 |  | 5.865
| 1 | 8.5 | 1.6 | 0.35 |  | 4.76
| 1 | 3.34 | 1.6 | 0.35 |  | 1.8704
| 1 | 3.34 | 3 | 0.23 |  | 2.3046
| 1 | 5.38 | 3 | 0.23 |  | 3.7122
| 1 | 3.1 | 3 | 0.23 |  | 2.139
| 1 | 2.894 | 3 | 0.23 |  | 1.9969
| 1 | 2.094 | 3 | 0.23 |  | 1.4449
| 1 | 11.6 | 3 | 0.23 |  | 8.004
| 1 | 4.912 | 3 | 0.23 |  | 3.3893
| 1 | 1.214 | 3 | 0.23 |  | 0.83766
| 1 | 2.4 | 3 | 0.23 |  | 1.656
| 1 | 1.406 | 3 | 0.23 |  | 0.97014
| 1 | 3 | 3 | 0.23 |  | 2.07
| 1 | 0.8 | 2.1 | 0.23 |  | 0.3864
| 2 | 1.2 | 0.9 | 0.23 |  | 0.4968
[5 empty] | cum | 61.7353 | 6000 | 370411.542
Single mala plaster |  |  |  |  | sq ft | 4559.62 | 30 | 136788.6
Double coat plaster |  |  |  |  | sqft | 874.57 | 45 | 39355.65
Casting |  |  |  |  | cum | 7.2218 | 5000 | 36108.7511
Steel |  |  |  |  | kg | 1020 | 90 | 91800
Shuttering |  |  |  |  | sq ft | 510 | 120 | 61200
Rebaring | [7 empty] | 2600
Wall tiles |  |  |  |  | sqft | 2778.45 | 80 | 222276
Kota | 1 | 14.8 | 8.2 |  | sq m | 121.36
| Deduction |  |  |  |  | -12.136
| 2 | 3 | 1.75 |  |  | 5.25
[6 empty] | 114.474 | 90 | 111062.6748
Green marble |  |  |  |  | sq ft | 142.76 | 110 | 15703.6
Moulding |  |  |  |  | r ft | 245 | 22 | 5390
Girder plate |  |  |  |  | kg | 240 | 145
Fabrication labour
Kitchen shed |  |  |  |  | kg | 398 | 130 | 51740
Patra |  | 8.6 | 4.14 |  | sq ft | 383.099 | 0 | 0
Damar sheet |  |  |  |  | sq ft | 383.099 | 23 | 8811.2779
Manglorian tiles |  |  |  |  | sq ft | 383.099 | 60 | 22985.9424
Breaking and cleaning | [7 empty] | 90000
1266234.0382

## Old Spa
Sr. No. | Description of Work | Unit | Final Rate | RA 01 | Amount Ra-01
1 | Fabrication structure | Kg | 130 | 6500 | 845000
2 | Cement sheet | Sq Ft | 90 | 2557.72 | 230194.8
3 | Tar Sheet (2mm) | Sq Ft | 200 | 2557.72 | 511544
4 | Manglorian Tiles | Sq Ft | 60 | 2557.72 | 153463.2
5 | RCC Slab | Lumpsum |  | 1 | 700000
6 | Masonry | Cu Ft | 169.9235 | 1899.75 | 322812.2345
7 | Double coat sand faced plaster | Sq Ft | 45 | 3582.71 | 161221.95
8 | Single mala plaster | Sq Ft | 30 | 3441.61 | 103248.3
9 | Colour | Sq Ft |  | 7040 | 0
10 | Flooring (Kota Rough Finish) (2'x2' kota) | Sq Ft |  | 3725 | 0
11 | Green Kesariya | Sq ft | 110 | 800 | 88000
12 | Moulding | Rft | 25 | 900 | 22500
13 | Electric (MK Switches and RR Kabel) | Lumpsum | 0 | 1 | 0
14 | Waterproofing (brickbed + chinamosiac) | Sq Ft | 230 | 640 | 147200
15 | Plumbing (Astral/Prince) - 10kg pipe | Lumpsum | 0 | 1 | 0
16 | Plumbing (Astral/Prince) - 6kg pipe | Lumpsum | 0 |  | 0
17 | Glade slab breaking and recasting | R.m. | 1200 | 26.17 | 31404
18 | Beams casting (100mmx300mm) | R.ft. | 490 |  | 0
19 | Beams casting (230mmx300mm) | R.ft. | 490 |  | 0
20 | Beams casting (300mmx450mm) | R.ft. | 735 |  | 0
| Grand Total ( Payable Amount ) |  |  |  | 3316588.4845

## New Spa
Sr. No. | Description of Work | Unit | Final Rate | RA 01 | Amount Ra-01 | RA 02 | Amount Ra-02 | RA 03 | Amount Ra-03 | Total Qty | Total Amount
1 | Fabrication structure | Kg | 130 | 4205 | 546650 |  | 0 |  | 0 | 4205 | 546650
2 | Cement sheet | Sq Ft | 90 | 1347.66 | 121289.4 |  | 0 |  | 0 | 1347.66 | 121289.4
3 | Tar Sheet (2mm) | Sq Ft | 200 | 1347.66 | 269532 |  | 0 |  | 0 | 1347.66 | 269532
4 | Manglorian Tiles | Sq Ft | 60 | 1347.66 | 80859.6 |  | 0 |  | 0 | 1347.66 | 80859.6
5 | RCC Slab | Sq Ft | 0 | 1 | 0 |  | 0 |  | 0 | 1 | 0
6 | Masonry | Cu Ft | 169.9235 | 15.61 | 2652.5064 |  | 0 |  | 0 | 15.61 | 2652.5064
7 | Double coat sand faced plaster | Sq Ft | 45 |  | 0 |  | 0 |  | 0 | 0 | 0
8 | Single mala plaster | Sq Ft | 30 |  | 0 |  | 0 |  | 0 | 0 | 0
9 | Colour | Sq Ft | 75 |  | 0 |  | 0 |  | 0 | 0 | 0
10 | Flooring (Kota Rough Finish) (2'x2' kota) | Sq Ft | 90 |  | 0 |  | 0 |  | 0 | 0 | 0
11 | Electric (MK Switches and RR Kabel) | Lumpsum | 125000 |  | 0 |  | 0 |  | 0 | 0 | 0
12 | Waterproofing (brickbed + chinamosiac) | Sq Ft | 230 |  | 0 |  | 0 |  | 0 | 0 | 0
13 | Plumbing (Astral/Prince) - 10kg pipe | Lumpsum | 205000 |  | 0 |  | 0 |  | 0 | 0 | 0
14 | Plumbing (Astral/Prince) - 6kg pipe | Lumpsum | 174000 |  | 0 |  | 0 |  | 0 | 0 | 0
15 | UGWT tank | L | 11 | 50000 | 550000 |  | 0 |  | 0 | 50000 | 550000
16 | Septic tank | L | 11 | 18000 | 198000 |  | 0 |  | 0 | 18000 | 198000
17 | Soak pit | Lumpsum | 45000 | 1 | 45000 |  | 0 |  | 0 | 1 | 45000
18 | Stone wall (material) | Tonnes | 850 |  | 0 |  | 0 |  | 0 | 0 | 0
19 | Stone wall (labour) | Sq Ft | 180 |  | 0 |  | 0 |  | 0 | 0 | 0
20 | Glade slab breaking and recasting | R.m. | 1740 |  | 0 |  | 0 |  | 0 | 0 | 0
21 | Beams casting (100mmx300mm) | R.ft. | 490 |  | 0 |  | 0 |  | 0 | 0 | 0
22 | Beams casting (230mmx300mm) | R.ft. | 490 |  | 0 |  | 0 |  | 0 | 0 | 0
23 | Beams casting (300mmx450mm) | R.ft. | 735 |  | 0 |  | 0 |  | 0 | 0 | 0
24 | Excavation (upto 2m) | Cu.Ft. |  |  | 0 |  | 0 |  | 0 | 0 | 0
25 | Backfilling excavated earth (with disposal within 100m from site location) | Cu.Ft. | 7 |  | 0 |  | 0 |  | 0 | 0 | 0
| Grand Total ( Payable Amount ) |  |  |  | 1813983.5064 |  | 0 |  | 0 |  | 1813983.5064

## China mosiac
China Mosiac
| Area | Rate | Total
Kitchen | 1328 | 230 | 305440
Store | 1705 | 230 | 392150
697590

## Pool
Lumpsum agreed |  | 2060000
Heat pump
| Number | L | B | H |  | Measurement | Rate | Total cost
Slab | 1 | 1.92 | 1.2 | 0.1 | cum | 0.2304 | 5000 | 1152
Steel | 1 |  |  |  | kg | 49.5821 | 90 | 4462.3872
Brickwork | 2 | 1.92 | 1.5 | 0.23 | cum | 1.3248
| 2 | 0.97 | 1.5 | 0.23 | cum | 0.6693
[5 empty] | cum | 1.9941 | 6000 | 11964.6
Plaster | 1 | 6.24 |  | 0.9 | sq m | 60.4282 | 30 | 1812.8448
19391.832
Electrical pipes | [7 empty] | 2700

## Roofing
| Patra | Damar sheet | Manglorian tiles (without material) | Manglorian tiles (only material)
Room 1 |  | 1200 | 1200 | 1200
Room 2 |  | 1200 | 1200 | 1200
Room 3 |  | 1200 | 1200
Room 4 |  | 1200 | 1200
Room 5 |  | 1200 | 1200
Room 6 |  | 1200 | 1200
Room 7 |  | 1200 | 1200 | 1200
Room 8 |  | 1200 | 1200
Room 9 |  | 1200 | 1200
Room 10 |  | 1200 | 1200
Room 11 |  | 1200 | 1200
Room 12 |  | 1200 | 1200
Room 13 |  | 1200 | 1200
Room 14 |  | 1200 | 1200
Dining |  | 1750 | 1600
Reception |  | 3550 | 3550
Total | 22100 | 22100 | 21950 | 3600
Rate | 22 | 23 | 34 | 26
Total cost | 486200 | 508300 | 746300 | 93600

## Gym
Gym
| Number | L | B | H |  | Measurement | Rate | Total cost
Filling | 1 | 3.04 | 10.67 | 0.25 | cum | 8.1092 | 150 | 1216.38
PCC | 1 | 8.23 | 11.28 | 0.1 | cum | 9.2834 | 3500 | 32492.04
Grade slab | 1 | 8.23 | 11.28 | 0.125 | cum | 11.6043 | 4000 | 46417.2
Steel |  |  |  |  | kg | 998.8981 | 90 | 89900.833
Brickwork | 2 | 3.04 | 0.23 | 0.25 | cum | 0.3496
| 1 | 10.67 | 0.23 | 0.25 | cum | 0.61352
[5 empty] | cum | 0.96313 | 6000 | 5778.75
175805.203
Tent Roof
| Number | L | B | H |  | Measurement | Rate | Total cost
Patra | 1 |  |  |  |  | 1400 | 22 | 30800
Damar sheet | 1 |  |  |  |  | 1400 | 23 | 32200
Fabrication steel | 1 |  |  |  |  | 1024 | 130 | 133120
Cutting | [7 empty] | 7200 | 3 days 3 labour
203320

## Misc work
GEB Otla
| Number | L | B | H |  | Volume (cum) | Rate | Total cost
Excavation | 1 | 8.8 | 0.9 | 0.7 | cum | 5.544 | 300 | 1663.2
Filling | 1 | 1.74 | 1.74 | 2.1 | cum | 6.358 | 150 | 953.694
Brickwork | 2 | 2.17 | 0.35 | 0.9 | cum | 1.3671
| 2 | 2.2 | 0.35 | 0.9 | cum | 1.386
| 4 | 2.17 | 0.23 | 2.1 | cum | 4.1924
| 2 | 1.74 | 0.23 | 2.1 | cum | 1.6808
[5 empty] | cum | 8.6264 | 6000 | 51758.28
Plaster | 4 | 2.2 |  | 2.1 | sq m | 18.48 | 323.4 | 5976.432
60351.606
STP Otla
| Number | L | B | H | Unit | Measurement | Rate | Total cost
Excavation | 1 | 20 | 0.9 | 0.75 | cum | 13.5 | 300 | 4050
Filling | 1 | 4.57 | 5.33 | 0.6 | cum | 14.6149 | 150 | 2192.229
Brickwork | 2 | 4.61 | 0.45 | 1.52 | cum | 6.3065
| 2 | 5.4 | 0.45 | 1.52 | cum | 7.3872
[5 empty] | cum | 13.6937 | 6000 | 82162.08
Plaster | 1 | 5.4 | 4.61 | 0.6 | sq m | 12.012 | 323.4 | 3884.6808
Grade slab | 1 | 4.61 | 5.4 | 0.125 | cum | 3.1118 | 4000 | 12447
Steel |  |  |  |  | kg | 268.3573 | 90 | 24152.1588
Fabrication | 1 | 5.81 | 6.6 |  | lumpsum |  |  | 0 | 2 days 4 karigar
Damar sheet |  |  |  |  | sq ft | 413.3699 | 23 | 9507.5072
Patra |  |  |  |  | sq ft | 413.3699 | 0 | 0
Cement bags |  |  |  |  | bags | 5 | 390 | 1950
Bricks |  |  |  |  | numbers | 475 | 9 | 4275
Reti |  |  |  |  | T | 1 | 800 | 800
145420.6558
DG Otla
| Number | L | B | H | Unit | Measurement | Rate | Total cost
Excavation | 1 | 8.2 | 0.9 | 0.7 | cum | 5.166 | 300 | 1549.8
Filling | 1 | 2.6 | 56 | 0.75 | cum | 109.2 | 150 | 16380
Brickwork | 1 | 2.6 | 0.35 | 0.88 | cum | 0.8008
| 1 | 5.6 | 0.35 | 0.88 | cum | 1.7248
| 1 | 2.6 | 0.23 | 0.65 | cum | 0.3887
| 1 | 5.6 | 0.23 | 0.65 | cum | 0.8372
| 1 | 2.8 | 1.9 | 0.115 | cum | 0.6118
[5 empty] | cum | 4.3633 | 6000 | 26179.8
Plaster | 1 |  |  |  | sq ft | 260 | 30 | 7800
PCC | 1 | 2.6 | 5.6 | 0.1 | cum | 1.456 | 3500 | 5096
Grade slab | 1 | 2.6 | 5.6 | 0.125 | cum | 1.82 | 4000 | 7280
Steel |  |  |  |  | kg | 313.3312 | 90 | 28199.808
Random | 1 | 2.6 | 5.6 |  | sq ft | 156.6656 | 70 | 10966.592
Fabrication | 1 |  |  |  | kg | 30 |  |  | Made from wastage
Fabrication | 1 |  |  |  | sq m | 0 | 6400 | 6400 | 2 days 4 karigar
Damar sheet |  |  |  |  | sq ft | 393.43 | 23 | 9048.89
Patra |  |  |  |  | sq ft | 393.43 | 0 | 0
Manglorian tiles | 1 |  |  |  | sq ft | 393.43 | 34 | 13376.62
132277.51
Tank near Kitchen
| Number | L | B | H |  | Volume (cum) | Rate | Total cost
Excavation | 1 | 1.67 | 1.67 | 1.65 | cum | 4.6017 | 300 | 1380.5055
PCC | 1 | 1.67 | 1.67 | 0.1 | cum | 0.27889 | 3500 | 976.115
Brickwork | 2 | 1.67 | 1.65 | 0.23 | cum | 1.2675
| 2 | 1.21 | 1.65 | 0.23 | cum | 0.91839
[5 empty] | cum | 2.1859 | 6000 | 13115.52
Plaster |  |  |  |  | sq m | 7.92 | 30 | 237.6
15709.7405
Wall near kitchen
| Number | L | B | H |  | Volume (cum) | Rate | Total cost
Excavation | 1 | 3.66 | 0.9 | 0.6 | cum | 1.9764 | 300 | 592.92
Brickwork | 1 | 3.66 | 0.45 | 1.35 | cum | 2.2235
| 2 | 3.66 | 1.75 | 0.15 | cum | 1.9215
| 2 | 1.75 | 0.35 | 0.23 | cum | 0.28175
[5 empty] | cum | 4.4267 | 6000 | 26560.2
Plaster |  |  |  |  | sq ft | 206 | 30 | 6180
33333.12
Bridge & Tent
| Number | L | B | H |  | Volume (cum) | Rate | Total cost
Brickwork | 2 | 6.75 | 0.35 | 0.58 | cum | 2.7405
[5 empty] | cum | 2.7405 | 6000 | 16443
Plaster |  |  |  |  | sq ft | 213.47 | 30 | 6404.1
Cleaning and breaking | [7 empty] | 2000
Tent kota | [7 empty] | 3500 | 2 mistry 4 labour
28347.1
Reception
| Number | L | B | H |  | Measurement | Rate | Total cost
Brickwork | 4 | 1.7 | 0.85 | 0.35 | cum | 2.023
[5 empty] | cum | 2.023 | 6000 | 12138
Plaster |  |  |  |  | sq ft | 201.85 | 30 | 6055.5
Electric jari filling | [7 empty] | 2000 | 1 mistry 2 labour
Green marble | 1 | 3.35 | 0.95 |  |  | 3.1825 | 110 | 3766.807
23960.307
Dining entrance
| Number | L | B | H |  | Measurement | Rate | Total cost
Damar sheet |  | 4.4 | 3.3 |  | sq ft | 156.2352 | 23 | 3593.4096
Patra |  |  |  |  | sq ft | 156.2352 | 0 | 0
Manglorian tiles |  |  |  |  | sq ft | 156.2352 | 60 | 9374.112
Dining top fabrication |  |  |  |  | kg | 105 | 130 | 13650
26617.5216
Random flooring
| Number | L | B | H | Unit | Measurement | Rate | Total cost
Kitchen | 1 | 8.99 | 2.89 |  | sq ft | 280.0763 | 110 | 30808.3884
Reception | 1 | 2.075 | 3 |  | sq ft | 67.1055 | 90 | 6039.495
| 1 | 1.6 | 3 |  | sq ft | 51.744 | 90 | 4656.96
| 1 | 1.55 | 3 |  | sq ft | 50.127 | 90 | 4511.43
| 1 | 1.45 | 3 |  | sq ft | 46.893 | 90 | 4220.37
| 1 | 1.45 | 3 |  | sq ft | 46.893 | 90 | 4220.37
| 1 | 1.84 | 3 |  | sq ft | 59.5056 | 90 | 5355.504
| 1 | 1.76 | 3 |  | sq ft | 56.9184 | 90 | 5122.656
| 1 | 1.23 | 3.5 |  | sq ft | 46.4079 | 90 | 4176.711
| 1 | 1.85 | 2.7 |  | sq ft | 53.8461 | 90 | 4846.149
| 1 | 1.06 | 3 |  | sq ft | 34.2804 | 90 | 3085.236
| 1 | 0.91 | 3 |  | sq ft | 29.4294 | 90 | 2648.646
| 1 | 0.9 | 3 |  | sq ft | 29.106 | 90 | 2619.54
| 1 | 0.915 | 3 |  | sq ft | 29.5911 | 90 | 2663.199
| 1 | 0.925 | 5.5 |  | sq ft | 54.8432 | 90 | 4935.8925
| 1 | 1.375 | 4.98 |  | sq ft | 73.8161 | 90 | 6643.4445
| 1 | 1.15 | 4 |  | sq ft | 49.588 | 90 | 4462.92
| 1 | 1.875 | 3.5 |  | sq ft | 70.7437 | 90 | 6366.9375
| 1 | 1.45 | 3 |  | sq ft | 46.893 | 90 | 4220.37
| 1 | 1.175 | 4.5 |  | sq ft | 56.9993 | 90 | 5129.9325
| 1 | 2.92 | 3.5 |  | sq ft | 110.1716 | 90 | 9915.444
126649.5954
50% kota material used for reception was by client. But cement sand was provided by HSP. Hence we charge 60% of total billing for reception work.
Staff quarters bathroom
| Number | L | B | H | Unit | Measurement | Rate | Total cost
Breaking and cleaning | [7 empty] | 3000 | 6 days 1 labour
Wall tiles | 1 | 7.25 |  | 2.3 | sq ft | 179.423 | 80 | 14353.84
Bottom flooring | 1 | 2.5 | 1.6 |  | sq ft | 43.04 | 80 | 3443.2
Frame | 1 | 0.3 | 0.3 |  | sq ft | 3.8808
|  | 0.75 | 0.28 |  | sq ft | 9.0384
Table top | 2 | 0.75 | 0.5 |  | sq ft | 8.07
Moulding |  |  |  |  | sq ft
Patra |  | 2.8 | 1.9 |  | sq ft | 57.3496 | 0 | 0
Manglorian tiles |  |  |  |  | sq ft | 57.3496 | 34 | 1949.8864
22746.9264
Hari plumber
| Number | L | B | H | Unit | Measurement | Rate | Total cost
Chamber | 3 | 2 | 2 | 1.5 | cum | 0.50977
Bricks | [5 empty] | 254.8853 | 9 | 2293.9677
Cement |  |  |  |  | bags | 5 | 390 | 1950
Pipes for Room 4,5,6 | [8 empty] | Yet to be added
4243.9677
Room 10 Overflow channel repairing
Material bill | [7 empty] | 7380
Bond tide | [7 empty] | 770
Labour | [7 empty] | 1600
Misc | [7 empty] | 500
10250